## Executive Dashboard
LCX US — Master Strategy: The Four Workstreams
Synthesis of Phases 1–4 · 23 July 2026 · Confidential — internal
Mission: launch LCX US as an easy-to-use US spot exchange where LCX sits in the middle as principal (buys/sells from liquidity providers, sells to users), custody stays at LCX, and the DeFi product line (Wallet / DEX / Chain) sits alongside. Four workstreams make it real. Scores are capability-based (1–5); commercial terms and all legal/licensing items require RFIs and counsel.
Phase | Objective | Headline recommendation | Top pick(s) | North-star metric | Gating dependency
1 · Liquidity Partners | LPs equal-to-or-better than B2C2; LCX-in-the-middle; +OTC/RFQ/options; custody at LCX | Go multi-LP: keep B2C2 anchor, add FalconX + Cumberland; Talos overlay; settle via Fireblocks off-exchange | FalconX (4.69), Cumberland (4.57), B2C2 (4.37) | Weekly volume routed / spread quality | Exchange model (CLOB vs RFQ); off-exchange settlement
2 · Payment Rails | US on/off-ramp: USD fiat + USDC/stablecoins; compliant; custody at LCX | Hybrid: rent to launch (sponsor bank + Circle Mint), build MTL footprint in parallel | Cross River (bank) + Circle Mint (USDC); Zero Hash (rent option) | Funded accounts; deposit success rate | Build-vs-rent licensing; BSA officer; GENIUS stablecoin policy
3 · Waitlist Growth | Grow the 4-July waitlist + convert at launch; paid + unpaid | Sequence: warm base → referral loop → crypto-native ads → mainstream (gated) | Existing base (4.82), Referral (4.55), Crypto-native ads (4.00) | Waitlist size; verified→funded rate; viral coefficient | Reward model (non-token); ad-platform certification (ties Phase 2)
4 · Listing Business | What blocks US listings + how to start | Hybrid: non-security majors now; build toward broker-dealer + ATS / RWA | Path C Hybrid (4.05); adopt Token Transparency Framework | # compliant listings; listing-committee throughput | Securities counsel; classification; BD/ATS; surveillance
The critical path in one line:
Phases 1 + 2 are the foundation (they make the exchange trade and move money) → Phase 4 sits on top of both plus counsel → Phase 3 runs in parallel but its reach and its paid ads are gated by Phase 2 licensing. One hire — the BSA/Compliance Officer — is the single most common critical-path dependency (Phases 2 and 4).

## Scorecards
Consolidated scorecards — all four phases
Weighted, capability-based (1–5). Values pre-computed. See phase dossiers for methodology & weights.
Phase 1 — Liquidity Providers (vs B2C2 baseline)
Provider | Weighted /5 | Tier
FalconX | 4.69 | Tier 1
Cumberland (DRW) | 4.57 | Tier 1
B2C2 (baseline) | 4.37 | Tier 1
Galaxy Digital | 4.16 | Tier 2
GSR | 4.1 | Tier 2
Wintermute | 4.05 | Tier 2
Flowdesk | 3.65 | Tier 3
Keyrock | 3.63 | Tier 3
DV Chain | 3.53 | Tier 3
Phase 2 — Payment-rails architecture options
Option | Weighted /5 | Verdict
D. Hybrid (rent to launch, build in parallel) | 4.17 | Recommended
C. Full build (own MTLs) | 3.88 | End-state
A. Rent — embedded (Zero Hash) | 3.79 | Fast, cedes custody/economics
B. Sponsor-bank direct + Circle Mint | 3.66 | Strong, needs MTLs
Phase 3 — Waitlist channels
Channel | Weighted /5 | Tier
Existing LCX base | 4.82 | Tier 1
Referral / queue-jump loop | 4.55 | Tier 1
Crypto-native ad networks | 4 | Tier 1
X + community | 3.85 | Tier 2
KOL cohort (vested) | 3.85 | Tier 2
Newsletter sponsorships | 3.78 | Tier 2
App-store pre-registration | 3.67 | Tier 2
Kaito Studio / attention | 3.48 | Tier 3
Paid KOL | 3.48 | Tier 3
PR | 3.45 | Tier 3
SEO / content | 3.37 | Tier 3
Google/Meta/X paid (gated) | 3.06 | Tier 3 / later
Phase 4 — Listing-business paths
Path | Weighted /5 | Verdict
C. Hybrid — non-security now, build toward BD/ATS | 4.05 | Recommended
A. Non-securities only | 3.95 | Launch path
B. Broker-dealer + ATS (securities) | 2.8 | Medium-term unlock

## Decisions Register
Consolidated decisions register — 24 decisions across the four phases
Recommendation = my suggested option; final calls are yours. Legal items pending counsel.
Phase | # | Decision | Options | Recommendation | Owner | Status
P1 | 1 | Exchange model | CLOB + LP market-making / riskless-principal RFQ | Confirm — RFQ/riskless-principal to launch; reconcile 'segregated order books' | Product / Anurag | Open
P1 | 2 | Launch asset scope | BTC/ETH/USDC + majors / broader alts / incl $LCX | BTC/ETH/USDC + top majors first | Product | Open
P1 | 3 | Sourcing architecture | Direct multi-LP / Talos-first / hybrid | Hybrid: direct B2C2+FalconX+Cumberland, Talos overlay later | BD / Eng | Open
P1 | 4 | Settlement / custody | Fireblocks OES / Copper / BitGo / pure self-custody | Fireblocks off-exchange settlement (B2C2 already on it) | Eng / Security | Open
P1 | 5 | Keep B2C2 as anchor | Yes / replace | Yes — anchor, onboarding underway | BD | Open
P1 | 6 | Number of LPs at launch | 2 / 3 / 4+ | 3 (B2C2 + FalconX + Cumberland) | BD | Open
P2 | 7 | Build vs rent licensing | Rent-first hybrid / full build | Rent-first hybrid; build MTLs in parallel | Compliance / Legal | Open
P2 | 8 | Fiat: bank vs embedded | Sponsor bank + Circle Mint / Zero Hash / both | Sponsor bank + Circle Mint (custody at LCX) | BD / Eng | Open
P2 | 9 | State scope at launch | Beachhead (excl NY) / all states | Beachhead set, exclude NY at launch | Compliance | Open
P2 | 10 | Stablecoin list | Adopt GENIUS policy / other | USDC anchor + PYUSD/USDG/USAT; hold USDT; exclude USD1 | Compliance / Product | Open
P2 | 11 | USDC rail | Circle Mint direct / via provider | Circle Mint direct (no spread) | Eng / Treasury | Open
P2 | 12 | Instant rails at launch | ACH+wire / +FedNow+RTP / +card aggregators | ACH+wire baseline; add FedNow/RTP; card via aggregators | Eng | Open
P3 | 13 | Paid budget | Lean $25k / Base ~$100k / Aggressive $300k | Base ~$100k (scale to Aggressive on proof) | Marketing | Open
P3 | 14 | Reward model | Position/non-cash / include token or points | Position / non-cash only (avoid securities line) | Legal / Marketing | Open
P3 | 15 | Waitlist target & deadline | e.g. 25k / 50k by launch | Set 25k by launch as base target | Marketing | Open
P3 | 16 | State scope for invites | Licensed-states beachhead / all-US | Licensed-states beachhead (mirror P2) | Marketing / Compliance | Open
P3 | 17 | Waitlist / referral tool | Viral Loops / KickoffLabs / EarlyParrot | Viral Loops (most mature) | Marketing / Eng | Open
P3 | 18 | Mainstream-paid timing | Gate on certification / push early | Gate on 'Verified Crypto Advertiser' + licence | Growth | Open
P4 | 19 | Listing path | Hybrid / non-security-only / BD+ATS now | Hybrid (C) — non-security now, build toward BD/ATS | Exec / Legal | Open
P4 | 20 | Launch listing set | BTC/ETH/USDC + majors; incl $LCX? | BTC/ETH/USDC + vetted handful; $LCX only with counsel | Legal / Product | Open
P4 | 21 | Securities counsel | External firm / in-house | External securities firm now | Legal / Monty | Open
P4 | 22 | Surveillance vendor | Solidus Labs / Eventus / Nasdaq | Solidus Labs (crypto-native leader) | Compliance / Eng | Open
P4 | 23 | Adopt Token Transparency Framework | Yes / internal-only | Yes — industry standard, institutional trust | Product / Legal | Open
P4 | 24 | Sequencing vs CLARITY | Proceed under current law / wait | Proceed under current law; treat CLARITY as upside | Exec / Legal | Open

## Risks & Dependencies
Consolidated risks & cross-phase dependencies
Severity = impact if unmanaged. Confirm legal items with counsel.
Phase(s) | Risk / dependency | Severity | Mitigation | Owner
P4 | Token misclassification (listing a security) | Critical | Counsel-opinion gate; non-security-first; adopt TTF | Securities counsel
P1/P2/P4 | US entity & licensing not yet in place (MSB/MTL; BD/ATS) | Critical | Rent-first + beachhead states; build footprint; counsel | Compliance / Legal
P2/P4 | BSA/Compliance Officer still to hire | High | Prioritise the hire — it gates go-live in two phases | Exec / HR
P2 | GENIUS stablecoin permissibility | High | Support only permitted coins; hold USDT; exclude USD1; counsel | Compliance
P1 | Counterparty / credit risk at LPs | High | Off-exchange settlement + spread flow across 3 LPs | Eng / Trading
P2 | Banking concentration (post-2023 failures) | High | Primary + backup sponsor bank | BD / Finance
P3 | Reward design crosses securities line | High | Non-token/position rewards; counsel on any token element | Legal / Marketing
P3 | Mainstream paid gated by certification + licence | Medium | Front-load crypto-native/organic; turn on big paid later | Growth
P1 | Exchange-model ambiguity (CLOB vs RFQ) | Medium | Decide before integration; drives API & settlement | Product
P2/P3 | Fraud (ACH returns, card chargebacks) | Medium | Plaid Signal + 7-day holds; optional underwriter | Risk / Eng
P4 | $LCX self-listing conflict/optics | High | Independent legal opinion + governance controls | Securities counsel
All | Cross-phase sequencing (P4 needs P1+P2; P3 reach needs P2) | High | Run P1+P2 in parallel; P3 alongside; P4 after foundation | Program mgmt

## Master Roadmap
Integrated roadmap — workstream × time window
Indicative sequencing; adjust to the launch date. ● = primary focus.
Workstream | Now / 0–3 months | 3–6 months | 6–12 months | 12–24 months
P1 Liquidity | ● Finish B2C2 onboarding; RFI FalconX + Cumberland; pick model; set up Fireblocks OES | ● 3-LP liquidity live; hedging/RFQ tuned | Talos overlay if breadth needed; add alternates | Deepen options/derivatives flow
P2 Rails | ● Hire BSA officer; select sponsor bank + Circle Mint; MSB; beachhead MTLs | ● Fiat (ACH/wire) + USDC live in beachhead states | Expand MTL footprint; add FedNow/RTP | National footprint; evaluate own charter
P3 Waitlist | ● Waitlist page + referral loop; convert warm US base; crypto-native ads | ● Community + KOLs + newsletters; app pre-registration | Mainstream paid (post-certification); launch-wave conversion | Sustained growth engine; lifecycle CRM
P4 Listing | ● Engage securities counsel; listing policy + committee; pick surveillance; adopt TTF | ● List first non-security majors (BTC/ETH/USDC) once licensing+custody+surveillance ready | Expand non-security listings via TTF vetting | Pursue BD/ATS (or CFTC reg if CLARITY) → security tokens / RWAs
Milestones | Foundations set; RFIs out; counsel engaged | Exchange soft-launch: trade + fund + first listings | Full platform; broadened listings + states | Securities/RWA business; Liberty Chain tokenization tie-in

## Dependency Map
Cross-phase dependency map
Read: row 'depends on' column. ●=hard dependency · ○=soft/shared.
Depends on → | P1 Liquidity | P2 Rails | P3 Waitlist | P4 Listing | Shared
P1 Liquidity | — | ○ custody/settlement backbone |  |  | Fireblocks OES / custody
P2 Rails | ○ settlement backbone | — |  |  | Custody at LCX; BSA officer
P3 Waitlist |  | ● reach + paid ads gated by licensing/states | — |  | Compliance guardrails
P4 Listing | ● liquidity per listed asset | ● custody, banking, MSB/MTL |  | — | Securities counsel; BSA officer
Takeaway: P1 and P2 are foundational and run in parallel; P4 depends on both (plus counsel); P3 runs alongside but is capped by P2 licensing/state coverage. BSA officer + securities counsel are the shared critical-path items.

## Budget View
Indicative budget view (planning only — validate via RFIs/counsel)
Directional ranges from public benchmarks; not quotes. Many costs are spread/fee-based or provider-dependent.
Phase | Cost type | Indicative range | Model | Notes
P1 | LP pricing | Spread-based (no direct fee) | Per-trade spread | B2C2 = spread-only, no per-tx fee; confirm each LP via RFI
P1 | Integration + credit | Eng time + credit lines | One-off + ops | Multi-LP + OES integration; credit reduces pre-funding
P2 | Sponsor bank + provider | Setup + per-tx + monthly min | Rent / bank fees | Per-provider; confirm via RFI
P2 | Licensing (if building MTLs) | $50k–$500k+ per state; 7-figure national | Build | Avoided/deferred by renting provider/bank cover first
P2 | Compliance stack | KYC per-verification + Travel Rule SaaS | Per-use / SaaS | Sumsub/Persona + Notabene
P3 | Waitlist growth | Lean $25k / Base ~$100k / Aggressive $300k | Campaign | From the Phase-3 funnel model (editable)
P4 | Securities counsel | Retainer + per-opinion | Professional fees | Every listing needs an opinion
P4 | Surveillance | SaaS subscription | SaaS | Solidus/Eventus
P4 | BD/ATS (Path B) | Six–seven figures; 12–24 mo | Build/registration | Only if pursuing security tokens
Shared | BSA/Compliance Officer | Salary (critical hire) | Headcount | Gates Phases 2 & 4

## Sources
Consolidated key sources (Phases 1–4)
Full per-phase source lists are in each phase workbook. July 2026.
Phase | Source | URL
P1 | B2C2 market making & liquidity | https://www.b2c2.com/solutions/market-making-liquidity-provision
P1 | Cumberland (DRW) products | https://www.cumberland.io/products-we-trade
P1 | FalconX first CFTC-registered swap dealer | https://www.prnewswire.com/news-releases/falconx-becomes-first--only-cftc-registered-cryptocurrency-swap-dealer-301524909.html
P1 | Talos institutional trading / aggregation | https://www.talos.com/our-solutions/trading
P1 | Fireblocks / Copper off-exchange settlement | https://www.bitgo.com/resources/blog/bitgo-and-copper-launch-first-trading-model-with-off-exchange-settlement/
P2 | GENIUS Act guide (Paul Hastings) | https://www.paulhastings.com/insights/crypto-policy-tracker/the-genius-act-a-comprehensive-guide-to-us-stablecoin-regulation
P2 | USDC/USAT vs USDT compliance (CCN) | https://www.ccn.com/education/crypto/why-usat-and-usdc-are-genius-act-compliant-and-usdt-isnt/
P2 | Circle Mint (USDC mint/redeem) | https://www.circle.com/circle-mint
P2 | MTL requirements 2026 (Finextra) | https://www.finextra.com/blogposting/30783/money-transmitter-license-in-2026-requirements-costs-and-a-practical-roadmap-for-fintechs
P2 | Crypto-friendly US banks 2026 | https://www.datawallet.com/crypto/best-crypto-friendly-banks-usa
P3 | SEC/CFTC crypto classification guidance (Mar 2026) | https://www.ropesgray.com/en/insights/alerts/2026/03/sec-and-cftc-issue-landmark-joint-guidance-on-classification-of-crypto-assets
P3 | FTC influencer disclosure rules 2026 | https://www.webtonic.io/blog/ftc-guidelines-for-influencers-6-rules-to-stay-compliant-in-2026
P3 | Crypto ad benchmarks / CAC (HypeLab) | https://www.hypelab.com/blog/crypto-advertising-benchmarks-2026
P3 | Robinhood referral case study | https://viral-loops.com/blog/how-robinhoods-referral-built-a-1m-user/
P4 | CLARITY Act tracker (Latham) | https://www.lw.com/en/us-crypto-policy-tracker/legislative-developments
P4 | SEC Howey framework 2026 (WilmerHale) | https://www.wilmerhale.com/en/insights/client-alerts/20260324-the-secs-new-framework-for-crypto-assets-under-howey
P4 | Token Transparency Framework / Alliance (CoinDesk) | https://www.coindesk.com/markets/2026/05/27/crypto-s-biggest-exchanges-back-push-for-token-disclosure-standards-as-industry-courts-institutional-capital
P4 | Solidus Labs trade surveillance | https://www.soliduslabs.com/solutions/trade-surveillance