## Read Me
LCX US · Phase 3 — Waitlist Growth
Paid + unpaid growth engine for the LCX US waitlist · 23 Jul 2026 · Confidential — internal
Purpose | Grow the LCX US waitlist (opened 4 July) and convert it to funded accounts at launch, across paid and unpaid channels, inside US crypto-marketing rules.
Starting position | 50%+ of LCX.com traffic is already US (a warm base to convert first); a micro-KOL cohort is already sourced (vested + FTC-disclosed); PR runs via blockchainwire. These are the cheapest early wins.
Tabs
• Channel Scorecard | Weighted scoring of 12 paid & unpaid channels; priority tiers. Weights (row 4) adjustable.
• Funnel & Budget | Editable model (blue = inputs): budget × CAC → signups → verified → funded, with Lean/Base/Aggressive scenarios.
• Referral & Compliance | The compliant Robinhood-style referral design + the securities/FTC/ad-platform guardrails.
• 90-Day Plan | Week-by-week workstreams and owners.
• Tooling & Vendors | Waitlist/referral software, crypto ad networks, attention/KOL, newsletters, CRM, KYC.
• Sources | Every URL used, numbered.
Scoring key | 5=best · 1=weak. Weighted score /5.
IMPORTANT | CAC and conversion figures are PLANNING ASSUMPTIONS from public benchmarks (blue cells) — validate with live data. Compliance items (securities-safe rewards, FTC, ad-platform licensing, state gating) require counsel & compliance sign-off. Not legal advice.
Cross-phase dependency | Paid crypto ads on Google/Meta/X require advertiser certification + a licensed entity — that is gated by Phase 2 (licensing) and the LCX US entity. Channels that DON'T need platform certification (existing base, referral, crypto-native networks, newsletters, KOLs, community, PR, SEO, app pre-registration) can start now.

## Channel Scorecard
Channel Scorecard — paid & unpaid
Weighted scoring (1–5). Weights in row 4 adjustable. Sequence: warm/organic first, crypto-native paid next, mainstream paid last (gated by certification).
Channel | Type | Reach / scale | CAC efficiency | Speed to activate | Compliance ease (start now?) | Audience fit (US crypto) | Effort/cost (higher=easier) | Weighted /5 | Rank | Tier
Weight → |  | 18% | 22% | 15% | 15% | 15% | 15%
Existing LCX base (email / on-platform / CRM) | Unpaid | 4 | 5 | 5 | 5 | 5 | 5
Referral / queue-jump loop | Unpaid | 5 | 5 | 4 | 4 | 5 | 4
Crypto-native ad networks (HypeLab/Bitmedia/Coinzilla) | Paid | 4 | 4 | 4 | 4 | 5 | 3
X organic + community (Telegram/Discord) | Unpaid | 4 | 4 | 3 | 4 | 5 | 3
KOL / micro-KOL cohort (already sourced) | Unpaid/vested | 4 | 4 | 4 | 3 | 5 | 3
Newsletter sponsorships (Milk Road, Bankless, Defiant) | Paid | 4 | 3 | 4 | 4 | 4 | 4
App store pre-registration (Google Play / iOS) | Unpaid | 3 | 4 | 3 | 4 | 4 | 4
Kaito Studio / attention marketing | Paid | 4 | 3 | 3 | 3 | 5 | 3
Paid KOL campaigns | Paid | 4 | 3 | 4 | 3 | 4 | 3
PR (blockchainwire + tier-1 crypto media) | Unpaid/Paid | 3 | 3 | 4 | 4 | 3 | 4
SEO / content | Unpaid | 3 | 4 | 2 | 5 | 3 | 3
Google / Meta / X paid (mainstream) | Paid | 5 | 3 | 2 | 2 | 4 | 2
Channel notes
Existing LCX base (email / on-platform / CRM) | Warmest, cheapest. Convert the 50%+ US LCX.com audience first. Announce the waitlist in-app, by email, on login.
Referral / queue-jump loop | The engine. Robinhood-style position + double-sided perks. Compounds every other channel. Avoid pre-announced token rewards (securities risk).
Crypto-native ad networks (HypeLab/Bitmedia/Coinzilla) | On-chain / wallet-behaviour targeting; CAC ~50–70% below general channels; native CTR 0.5–3%. No platform certification needed. Start here for paid.
X organic + community (Telegram/Discord) | X = discovery/narrative; Telegram = activation; Discord = depth/retention. Consistent content + moderation.
KOL / micro-KOL cohort (already sourced) | Cohort already sourced & FTC-disclosed. Vested (non-cash) alignment; must disclose material connection.
Newsletter sponsorships (Milk Road, Bankless, Defiant) | Milk Road ~$10–25k/send, 330k subs. Native ads in-voice convert well; awareness + signups.
App store pre-registration (Google Play / iOS) | Google Play pre-reg up to 90 days → auto-push at launch. Feeds day-1 install velocity. Use the LCX org accounts.
Kaito Studio / attention marketing | Creator–brand marketplace across X/YT/TikTok + mindshare tracking. NOTE: 'yap-to-earn' sunset Jan 2026 — use Studio + KOLs, not post-to-earn.
Paid KOL campaigns | Beyond the vested cohort; must carry 'Paid Partnership' labels (X, from Feb 2026) + FTC disclosure; no return promises.
PR (blockchainwire + tier-1 crypto media) | Founder-led reshoring/American-DeFi story; coordinated drops. Awareness, not direct signups.
SEO / content | Slow but compounding; owns 'LCX US', 'American DeFi', on-ramp/self-custody intent terms.
Google / Meta / X paid (mainstream) | Largest reach but GATED: certified 'Verified Crypto Advertiser' + licensed exchange only; buy/sell promos restricted. Turn on AFTER certification/licensing.

## Funnel & Budget
Funnel & Budget model — planning assumptions (blue = editable input)
Signups = Budget ÷ CAC for paid; organic entered directly. Figures are planning estimates from public benchmarks — validate live.
BASE scenario — channel spend & signups
Channel | Type | Budget ($) | Signup CAC ($) | Signups
Crypto-native ad networks | Paid | 30000 | 35
Newsletter sponsorships | Paid | 25000 | 50
Paid KOL campaigns | Paid | 20000 | 45
Kaito Studio / attention | Paid | 10000 | 60
Google/Meta/X (post-cert) | Paid | 15000 | 90
Existing LCX base | Organic | 0 | — | 8000
Referral loop uplift | Organic | 0 | — | 6000
X + community | Organic | 0 | — | 2500
KOL cohort (vested) | Organic | 0 | — | 2000
App pre-registration | Organic | 0 | — | 1200
PR | Organic | 0 | — | 1500
SEO / content | Organic | 0 | — | 800
TOTAL
Funnel conversion (BASE)
Total waitlist signups
× Waitlist to verified (KYC) at launch |  | 55%
Verified users
× Verified to funded account |  | 45%
Funded accounts
Total spend
Blended CAC per funded account
Scenario summary (illustrative)
Scenario | Total budget ($) | Est. waitlist | Est. funded | Blended CAC/funded ($)
Lean | 25000 | 12000 | 3200
Base (model above)
Aggressive | 300000 | 55000 | 14000
Benchmarks (public): crypto-exchange signup CAC ~$100–200 general; crypto-native networks 50–70% lower (~$30–60); DeFi ~$85; wallet installs $15–40. Waitlist LP conversion ~15% (good 20–30%). These inform the blue inputs.

## Referral & Compliance
Referral mechanic design + compliance guardrails
Compliant, Robinhood-style. Confirm reward structure with securities counsel.
A. Referral mechanic (compliant)
Core loop | Every signup gets a unique link + a visible queue position + leaderboard. Referrals move you up. Position is the primary reward (Robinhood model: ~1M pre-launch signups, 3x viral coefficient, no cash reward).
Double-sided perks | Both referrer and referee get a non-cash perk (earlier access tier, launch fee-discount, status badge, LCX swag). Double-sided programs see ~3x the participation of single-sided.
Milestone ladder | Progressive, non-cash: 1 ref = move up; 3 = early-access tier; 10 = 'founding user' badge + higher launch fee discount; 25 = priority support / event invite.
First-60-seconds prompt | Confirmation email/screen immediately prompts sharing — the single biggest driver of loop velocity.
Anti-sybil | Maturation window: the larger perk unlocks only after the referred user completes KYC and stays active at launch. ML fraud detection; cap referrals; dedupe device/IP.
At launch (post-live) | Convert to a fee-based referral (trading-fee discount / rev-share), KYC-gated, min-activity qualified — the Coinbase/Kraken pattern (compliant, not a token giveaway).
B. Compliance guardrails
Guardrail | What it means | Risk if ignored | Src
No pre-announced token quid-pro-quo | SEC/CFTC (Mar 2026): airdrops with no bargained-for consideration aren't securities, but pre-announced 'do X to earn a token' IS. Keep waitlist rewards non-token / non-cash, or clear with counsel. | Unregistered securities offering | 1,8
FTC endorsement disclosure | Every KOL (paid, tokens, or early access) discloses the material connection clearly, before the fold; no guaranteed-return or risk-downplaying language. | FTC action; reputational | 6
No price / return promises | Per the LCX narrative: utility not investment. No 'buy now', ROI, or price talk in any waitlist creative. | Ad-platform rejection; securities/marketing risk | 7
Ad-platform certification | Google/Meta/X crypto ads need a certified 'Verified Crypto Advertiser' + licensed exchange; buy/sell promos restricted. | Ads auto-rejected; wasted spend | 3,4
Geo / state gating | Only invite & convert users in states LCX US can legally serve (ties to Phase 2 licensing). Geoblock others (EEA already geofenced). | Operating out of licence | —
Data & consent | Waitlist email capture with clear consent, privacy policy, CAN-SPAM unsubscribe; store PII per policy. | Privacy / CAN-SPAM exposure | —

## 90-Day Plan
90-Day waitlist growth plan
Indicative; adjust to launch date. Owners map to the LCX team.
Window | Workstream | Actions | Primary owner | KPI
Weeks 1–2 | Foundation | Stand up waitlist page + referral tool (queue/leaderboard); wire analytics/attribution; email welcome series; adopt compliant reward + guardrails. | Marketing / Eng | Page live; loop tested
Weeks 1–2 | Warm base | Announce to the 50%+ US LCX.com audience — email, in-app, login banner. | Marketing (Tanushree) | Base signups
Weeks 2–4 | Referral ignition | Launch double-sided perks + milestone ladder; seed leaderboard; first-60-sec share prompt. | Marketing | Viral coefficient >1
Weeks 2–6 | Crypto-native paid | Test HypeLab/Bitmedia/Coinzilla with on-chain targeting; optimise to cost-per-signup. | Growth / Adspirer | Paid CAC < $60
Weeks 3–8 | Community + KOL | Activate X/Telegram/Discord cadence; deploy the vested micro-KOL cohort (FTC-disclosed). | Community | Community growth
Weeks 4–8 | Newsletters + attention | Milk Road / Bankless / Defiant sends; Kaito Studio creators. | Marketing | Signups per send
Weeks 4–10 | PR + SEO + app pre-reg | blockchainwire + tier-1 drops; publish 'American DeFi / LCX US' content; open Google Play/iOS pre-registration. | Marketing / Eng | Coverage; pre-reg installs
Weeks 6–12 | Mainstream paid (if certified) | Once 'Verified Crypto Advertiser' + licence in place, turn on Google/Meta/X. | Growth | Scaled CAC
Launch window | Convert | Invite in waves by queue position; push app pre-reg; switch to fee-based referral; drive KYC → funded. | Whole team | Funded accounts

## Tooling & Vendors
Tooling & vendors
Shortlist by function.
Function | Options | Notes | Src
Waitlist / referral software | Viral Loops, KickoffLabs, EarlyParrot, Rally, LaunchList, Waitlister | Queue position + leaderboard + milestone rewards + fraud controls. Viral Loops most mature ($35/mo+/1k). | 2,5
Crypto-native ad networks | HypeLab, Slise, Bitmedia, Coinzilla, Cointraffic, Blockchain-Ads, Mintfunnel | On-chain/wallet targeting; native > display 2–3x; cost-per-on-chain-action tracking. Start paid here. | 9
Attention / creator | Kaito Studio (X/YT/TikTok marketplace + mindshare) | yap-to-earn sunset Jan 2026; use the creator marketplace, not post-to-earn. | 10
Newsletters | Milk Road (~$10–25k/send, 330k), Bankless, The Defiant | Native in-voice ads; awareness + signups. | 11
KOL management | In-house cohort (sourced) + platforms (theKOLLAB etc.) | Vested + FTC-disclosed; 'Paid Partnership' labels on X. | 6
CRM / email / attribution | (Existing LCX stack) + UTM + referral tool analytics | Welcome series (open 52–68% on email 1); track signup→verified→funded. | —
KYC / identity | Sumsub / Persona (from Phase 2) | Gate referral rewards on KYC to kill sybils. | —

## Sources
Sources
Public sources consulted, July 2026.
# | Source | URL
1 | SEC & CFTC joint interpretation on crypto (airdrops/consideration), Mar 2026 — Ropes & Gray | https://www.ropesgray.com/en/insights/alerts/2026/03/sec-and-cftc-issue-landmark-joint-guidance-on-classification-of-crypto-assets
2 | How Robinhood's referral built a 1M-user waitlist — Viral Loops | https://viral-loops.com/blog/how-robinhoods-referral-built-a-1m-user/
3 | Crypto advertising policies (Google/Meta/X) 2026 | https://www.acquire.fi/blog/crypto-advertising-policies
4 | Complete guide to crypto advertising 2026 — Coinbound | https://coinbound.io/a-complete-guide-to-crypto-advertising/
5 | Best pre-launch waitlist tools 2026 — Waitlister | https://waitlister.me/growth-hub/guides/best-pre-launch-waitlist-tools
6 | FTC influencer disclosure guidelines 2026 | https://www.webtonic.io/blog/ftc-guidelines-for-influencers-6-rules-to-stay-compliant-in-2026
7 | Compliant crypto paid advertising playbook 2026 — Surgence | https://surgence.io/blog/crypto-paid-advertising-playbook
8 | SEC crypto asset classification / Howey framework 2026 — WilmerHale | https://www.wilmerhale.com/en/insights/client-alerts/20260324-the-secs-new-framework-for-crypto-assets-under-howey
9 | Crypto ad benchmarks 2026 (CTR/CPM/CPA) — HypeLab | https://www.hypelab.com/blog/crypto-advertising-benchmarks-2026
10 | What is Kaito — Studio, Markets, yap-to-earn sunset — CoinGecko | https://www.coingecko.com/learn/what-is-kaito-earn-yap-points
11 | Milk Road newsletter sponsorship / strategy | https://newsletterbear.com/milk-road-case-study-crypto-ai-newsletter-strategy/
12 | Crypto user acquisition cost benchmarks 2026 — HypeLab | https://www.hypelab.com/blog/crypto-user-acquisition-cost-benchmarks-2026
13 | Waitlist benchmarks & conversion rates — GetWaitlist | https://getwaitlist.com/blog/waitlist-benchmarks-conversion-rates
14 | Crypto community growth (Telegram/Discord/X) 2026 | https://thekollab.io/articles/how-to-build-strong-crypto-community/
15 | Google Play pre-registration & ASO | https://appradar.com/academy/google-play-pre-registration-create-hype-for-apps-before-launch
16 | Crypto wallet referral program playbook / sybil controls 2026 | https://track360.io/blog/crypto-wallet-growth-referral-program-playbook-2026
17 | Coinbase / Kraken referral programs 2026 (US compliant) | https://www.bitget.com/academy/how-crypto-referral-bonuses-work-in-america-comprehensive-guide-2026
18 | X paid partnership / crypto promotion labels 2026 | https://www.legalnodes.com/article/crypto-ad-guidelines-meta-google-twitter